# 15. Resource Allocation and Requirements

The project will involve a small technical team, plus assistance from ShopWave staff at various times during the 24-week project plan. Not everybody will be involved throughout the project duration. For instance, the Business Analyst will be most involved during the requirements and design phase, while the testing team and customer support will have more responsibilities close to the launch. The Project Manager will assess staff availability and avoid conflicts with day-to-day business operations [3], [6].

## 15.1 Human Resource Requirements

| Role / resource | Main work and associated WBS tasks | Planned involvement |
| --- | --- | --- |
| Project Manager (PM) | Charter, management plan, final readiness, reporting and closure (1.1, 1.3-1.4, 5.1, 6.4) | Throughout all phases; coordinates work and budget |
| Business Analyst (BA) | Stakeholders, customer requirements, ticket review, FAQs and conversation design (1.2, 2.1-2.3, 2.5) | February-March mainly; assists with UAT |
| Head of IT / technical lead (IT) | Solution design approval, cloud setup oversight, launch, monitoring and handover (2.4, 2.6, 3.1, 5.2-5.3, 6.1, 6.5) | During design, development, deployment and handover |
| AI/NLP Engineer (AI) | Training chatbot, answer corrections and resolution of post-launch problems (3.2, 4.2, 6.2) | April-July mainly |
| Integration Developer (DEV) | CRM/Zendesk/order integrations, website/app widget and dashboard (3.4-3.6) | April-May mainly |
| QA/Test Lead (QA) | Answer testing, privacy, security and performance; defect tracking (4.1, 4.3) | May-June mainly |
| Head of Customer Service (CS) | Approval of knowledge base, organizing testing, training and feedback (3.3, 4.4-4.6, 6.3) | March-June; feedback during hypercare |
| Support agents / SMEs | Answer review, participation in UAT and training, escalated customer requests handling (4.4-4.5) | Part-time; staff allocated for agreed testing sessions |
| Privacy & Legal Officer (PLO) | Privacy impact assessment, data-use review and pre-production approval | Major reviews during design, testing and go-live |
| Platform vendor | Licenses, cloud/NLP platform consultations and escalation assistance (3.1, 5.3) | When required by the vendor agreement |

## 15.2 Technical and Other Resources

| Resource | Purpose / requirement | Availability period |
| --- | --- | --- |
| Cloud chatbot/NLP platform | Building, hosting, training and running the English-language support for top 40 enquiry types | Licensed before development; used during hypercare |
| Anonymized support ticket dataset | Identification of frequent queries and testing of expected answers without unnecessary personal data | Requirements, development and testing |
| Approved knowledge base | FAQs, return policies, product information and escalation | Draft during design; approved prior to chatbot training |
| System/API access | Controlled read-only order status access and CRM/Zendesk integrations | Development and integration |
| Development and test environments | Separate environments for development, testing and release checking; limited credentials | Development through launch |
| Test devices, tools and monitoring | Website/mobile app testing, defect tracking, uptime, answer quality and dashboard | Testing, launch and hypercare |
| Training materials and staff time | User guides, handover procedures and arranged agent training sessions | End May to June |

## 15.3 Budget Allocation

The budget as per the project charter is set at AUD 280,000. It consists of AUD 254,500 for project costs and AUD 25,500 contingency reserve. The allocation below is a budget proposal, not an expenditure record or any supplier quote. Further negotiations by the Project Manager and Finance team will be required for the confirmation of these figures [3], [6].

| Cost category | Proposal (AUD) | Budget coverage |
| --- | --- | --- |
| Project management and business analysis | 47,000 | Planning, requirements, coordination and reporting |
| AI/NLP engineering and knowledge base preparation | 72,000 | Model setup and tuning, chatbot answers preparation |
| Integration and application development | 57,000 | APIs, customer chat interface and analytics |
| Testing, security and privacy review | 30,000 | Functional/UAT, security, performance and compliance testing |
| Platform, cloud and development tools | 28,000 | Vendor licenses, cloud hosting and tools |
| Training, deployment and hypercare | 20,500 | Training materials and staff time, launch activities and post-launch assistance |
| BASELINE TOTAL | 254,500 | Project cost |
| Contingency reserve | 25,500 | For approved unforeseen project costs |
| APPROVED PROJECT TOTAL | 280,000 | Total budget |

Resource availability will be assessed each week during the project meeting. In case of any shortfall in an important task, the matter will be recorded as an issue. Any use of the contingency reserve will need to be processed as a change request [6].

# 16. Responsibility / RASCI Matrix

The RASCI matrix illustrates who will be responsible for each activity and for the decision-making on the completion. R stands for Responsible (the work will be done by this person), A – Accountable (responsible for the outcome of the work), S – Supporting, C – Consulted and I – Informed. One role should be accountable for each activity. The matrix follows the main activities in Ife’s WBS, while the separate tasks can be assigned in Jira [3], [6].

Abbreviations: PM = Project Manager; BA = Business Analyst; IT = Head of IT; AI = AI/NLP Engineer; DEV = Integration Developer; QA = QA/Test Lead; CS = Head of Customer Service; PLO = Privacy & Legal Officer; SP = Project Sponsor.

| WBS activity | PM | BA | IT | AI | DEV | QA | CS | PLO | SP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1–1.5 Charter and approval | R | S | C |  |  |  | C |  | A |
| 2.1–2.3 Requirements and FAQs | A | R | C |  |  | S | C | C | I |
| 2.4–2.6 Architecture, conversations and sign-off | C | R | A | S | S |  | C | C | I |
| 3.1 Cloud platform setup | I |  | A | S | R |  |  | C |  |
| 3.2 Chatbot build and training | I | C | A | R | S | S | C | C |  |
| 3.3 Knowledge-base approval | I | S | C | S |  |  | A / R | C |  |
| 3.4–3.6 Integrations, widget and dashboard | I | C | A | S | R | S | C | C |  |
| 4.1–4.3 Defect, security and performance tests | I | S | C | S | S | A / R | C | C |  |
| 4.4–4.6 UAT, training and sign-off | I | S | C |  | S | S | A / R | C |  |
| 5.1–5.3 Readiness and deployment | R |  | A | S | S | S | C | C | I |
| 6.1–6.3 Hypercare, fixes and feedback | I | S | A | R | S | S | R | C |  |
| 6.4–6.6 Handover and closure | R | S | R |  |  | C | C | C | A |

For the rows with “A/R” the same person completes and owns the activity. The sponsor will retain responsibility for major funding or scope approvals, even when not accountable for everyday work.

# 17. Risk and Issue Management

## 17.1 Risk Assessment Method

A risk is a potential event that may influence the project. The Project Manager will maintain the risk register and will analyze it on a weekly basis. Each risk is rated by two measures – its likelihood and potential impact from 1 (low) to 5 (very high). Multiplication of two scores provides a measure between 1 and 25: low = 1-5, medium = 6-12 and high = 15-25. These are only preliminary estimates and the team will need to modify them during the project progression [7].

## 17.2 Risk Register and Treatment

Main risks include inaccurate chatbot answers, privacy issues, system integration delays and problems affecting the go-live. The proposed controls are based on the AI Risk Management Framework and the Australian Privacy Principles [4], [8].

| ID / risk | L × I = score | Owner | Preventive / mitigating measures | Action upon occurrence |
| --- | --- | --- | --- | --- |
| R1 Inaccurate or misleading chatbot answers | 4 × 5 = 20 (High) | AI / CS | Using the approved sources for answers; testing of frequent and difficult questions; minimum 90% accuracy at UAT | Disabling of answers, escalation to an agent, correction of the content and retesting |
| R2 CRM, Zendesk or order system integration delays | 4 × 4 = 16 (High) | IT / DEV | Early verification of API permissions; building a test integration; tracking dependencies with IT | Priority of essential features and escalating schedule impacts to PM |
| R3 Personal information leakage via logs or chatbot answers | 3 × 5 = 15 (High) | PLO / IT | Minimization of personal data usage; access control and anonymization of tests; completion of privacy review | Restricted usage of the affected service; starting the incident procedure; notifying relevant officers |
| R4 Cloud platform or vendor outage | 3 × 4 = 12 (Medium) | IT | Confirmation of services arrangement; uptime monitoring; testing the fall-back paths | Customers switching to human support and contact of the vendor |
| R5 Customer support staff unavailability for UAT or training | 4 × 3 = 12 (Medium) | CS | Reserving of sessions in advance and arrangement of backup agents | Rebooking of the sessions; shift of the non-critical tasks; notification of PM |
| R6 Exceeding of the project budget | 3 × 4 = 12 (Medium) | PM | Tracking of the commitments and expenditures weekly; controlling scope additions | Analysis of over-expenditure; using only the approved contingency reserve |
| R7 Poor customer utilization or handover experience | 3 × 4 = 12 (Medium) | CS | Usability and agent handover testing; clear chatbot messages provision | Feedback analysis; improvement of flows; promotion of assisted support |
| R8 Critical defects close to 18 June launch | 3 × 5 = 15 (High) | QA / IT | Testing during development; prioritizing of defects; setting go/no-go criteria | Postponement or limitation of the release through approval process |

## 17.3 Risk Monitoring and Escalation

The risk register will contain risk name, score, risk owner, preventive actions, next review date and current status. High risks will be addressed at the weekly meeting and major milestones. In case a risk may potentially impact the project deadline, budget, security or privacy, it will be notified to the sponsor and the relevant technical lead immediately by the Project Manager. Once the risk turns into an issue, it will be recorded in the issue log [7], [8].

## 17.4 Issue Management Strategy

An issue is a problem that already occurred, such as API connection failure or error detection during testing. It will be reported by the person who noticed it promptly. The Project Manager will log it in Jira, assign the owner, define priority and target date and track the issue until the corrective action has been verified and issue closed [3], [6].

| Step | How it will be managed |
| --- | --- |
| 1. Log | Register issue ID, description, date of the discovery, affected WBS task, reporter and supporting evidence. |
| 2. Assess | Rate priority as Critical, High, Medium or Low according to impacts on security, customers, cost and schedule. |
| 3. Assign | Assign one owner to resolve the issue and set the realistic due date. |
| 4. Resolve | Root cause investigation, implementation of corrective or workaround and update of the Jira issue. |
| 5. Verify and close | QA or relevant business owner will verify the results; PM will close the issue and register the lessons learned. |
| 6. Escalate | Critical security/privacy issues and risks to go-live to be reported immediately to the Head of IT, Privacy Officer and PM; sponsor makes decisions on impacts or scope changes. |

## 17.5 Illustrative Issue Log

Following are the illustrative examples of how the team could handle issues throughout the project. They are hypothetical illustrations prepared for planning purposes only.

| Example ID / task | Issue and priority | Assigned owner | Action / closing evidence |
| --- | --- | --- | --- |
| I-01 / 3.4 | Order API returns incomplete status (High) | Integration Developer | Checking of mapping with IT; retesting of sample orders; attachment of the passed results |
| I-02 / 4.1 | Bot provides outdated returns policy (High) | AI Engineer / CS | Updating of the approved content; rerunning of the relevant test scripts |
| I-03 / 4.4 | Insufficient number of agents for UAT (Medium) | Head of Customer Service | Arrangement of the replacement session; confirmation of attendance and UAT sign-off |

An unresolved critical issue will prevent the chatbot launch until the appropriate corrective action has been implemented and approved. Any scope, schedule or budget change will be handled as the change request according to Section 18 [3], [8].

## References used in Sections 15-17 (continue numbering from the group's existing [1]-[5] list)

[3] Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK® Guide), 7th ed. Newtown Square, PA, USA: Project Management Institute, 2021. (Already included in the group reference list.)

[4] Office of the Australian Information Commissioner, "Australian Privacy Principles." [Online]. Available: https://www.oaic.gov.au/privacy/australian-privacy-principles. [Accessed: Oct. 20, 2026]. (Already included in the group reference list.)

[6] International Organization for Standardization, Project, programme and portfolio management—Guidance on project management, ISO 21502:2020, 2020. [Online]. Available: https://www.iso.org/standard/74947.html. [Accessed: Oct. 20, 2026].

[7] International Organization for Standardization, Risk management—Guidelines, ISO 31000:2018, 2018. [Online]. Available: https://www.iso.org/standard/65694.html. [Accessed: Oct. 20, 2026].

[8] National Institute of Standards and Technology, Artificial Intelligence Risk Management Framework (AI RMF 1.0), NIST AI 100-1, Jan. 2023. [Online]. Available: https://doi.org/10.6028/NIST.AI.100-1. [Accessed: Oct. 20, 2026].